4.0 Project Scope

The section provides clarity on what the SavePlate system will deliver and what it will not, identifying the boundaries of a SavePlate project. Defining the scope helps to avoid adding things at the last minute in development and helps maintain the team working on the projects agreed to.

4.1 In Scope

In this project the following features and functions will be developed and delivered:

Use Case 1: Register User and Privacy Settings

- A new account can be registered by users with their full name, email address, password, and optional household size.

- After successful registration, the system will send a 6-digit verification code in an email to activate the account.

- Users can securely log in with their email and password for registered users.

- Two-Factor Authentication (2FA) can be enabled in Account Settings to add to security.

- Users have the ability to manage their privacy settings, including control of visibility of their donation listing.

Use Case 2: Control Food Stocks

- Authenticated Users can add an item of food to their own inventory including Name, Quantity, Expiry Date, Category and Storage Location.

- Existing food inventory items can be dynamically edited and updated by users as time goes on.

- Food items are removable from the list and user can mark them as used when they are eaten.

- Flagging items that are near their expiration date can be done and they can be immediately turned into donation listings from the inventory screen.

Use Case 3: Browse Food Items

- With filter options for category, expiry date and storage type, users can browse through all available food listings, both personal and community food listings.

- All users can see detailed information about the listed food item, such as the name, quantity, expiry date and pick-up location.

- Users can use the ‘Used’ ‘Plan for Meal' and ‘Flag for Donation' options at the browse view.

- Users can pick up donation lists available from other households.

Use Case 4: Food Analytics

- The system generates a visual analytics dashboard showing the total amount of food saved from waste (in kg) and the number of donations made.

- Users can view analytics reports within a weeks or months and by foods category.

- Motivation is provided for further engagement through the use of progress indicators and summary cards.

Use Case 5: Navigate to View Notifications

- Also, the system automatically notifies via in-app and email when the food item is 3 days or less from its expiration date.

- Users are alerted about donation status (claimed, completed) and reminder about meal planning.

- All notifications can be displayed in a single panel, listing them from newest to oldest and marking as read.

- Each notification links directly to the screen on which the information is displayed.

Use case 6: Weekly eating plan

- Users can schedule a weekly menu on a 7-day calendar view featuring the foods they currently have in their pantry.

- They recommend recipes with the ingredients of the inventory available, giving preference to items that are about to expire.

- When you set up a meal plan, the necessary amounts of ingredients will be reserved in the inventory and reminders will be set up.

4.2 Out of Scope

These are not included in this initial version of SavePlate to ensure that the project is within scope and is achievable in the timeframe:

- Mobile application development (iOS or Android native apps) — there will only be a responsive Web app.

- Any online payment or business related food transactions.

- Integration with third party grocery stores or e-commerce stores.

- Very convenient automatic food item entry via scanning of barcode or QR code.

- Restaurant or hotel food waste management — system is focused on households.

- Recipe recommendation based on AI — only the recipe suggestions that are pre-defined and associated with the inventory, will be implemented.

- Multilingual (only English will be supported in this version).

- GPS tracking system to help locate food donation collection sites in real-time.

5. PROJECT SCHEDULE

This project follows an iterative and incremental development methodology. This project is developed by clear planning and design, the development of the application is completed in two iterations, testing and final submission.

Summary:

| S.N | Tasks | Description | Assigned to | Duration |
| --- | --- | --- | --- | --- |
| 1.0 | Project Initiation | Team setup and initial planning activities | All Members | 3 days |
| 1.1 | Team Formation & Role Assignment | Assign team leader, members, and individual responsibilities. | All Members | 1 day |
| 1.2 | Case Study Review | Read and analyse the SavePlate case study and use case diagram. | All Members | 1 day |
| 1.3 | GitHub Repository Setup | Create team GitHub repo and define branch naming conventions. | Anurodh | 1 day |
| 2.0 | Task 1 – Project Proposal | Write and submit the full project proposal document. | All Members | 25 days |
| 2.1 | Overview, Aims & Objectives | Write Sections 1, 2, and 3 of the proposal. | All Members | 3 days |
| 2.2 | Project Scope | Define in-scope and out-of-scope features based on the 6 use cases. | All Members | 2 days |
| 2.3 | WBS, Milestones & Gantt Chart | Create WBS table, milestone list, and Gantt chart using GanttProject. | Nabin | 3 days |
| 2.4 | Technical Description | Complete development and demonstration platform tables. | Anurodh | 2 days |
| 2.5 | Risk Management Plan | Identify risks, assess probability, and define mitigations. | All Members | 2 days |
| 2.6 | Review & Submission | Proofread final document and submit via HLMS by 12 June 2026. | All Members | 1 day |
| 3.0 | Task 2: Requirements & Design | Write and submit requirements specification and design document. | All Members | 13 days |
| 3.1 | Functional & Non-Functional Req. | Document all system requirements derived from the 6 use cases. | All Members | 3 days |
| 3.2 | User Stories: UC1 & UC2 | Epics, user stories, acceptance criteria, MoSCoW, and tasks. | Anurodh | 3 days |
| 3.3 | User Stories: UC3 & UC4 | Epics, user stories, acceptance criteria, MoSCoW, and tasks. | Nabin | 3 days |
| 3.4 | User Stories: UC5 & UC6 | Epics, user stories, acceptance criteria, MoSCoW, and tasks. | Dipti | 3 days |
| 3.5 | Architectural & Deployment Diagram | Create system architecture diagram using draw.io. | All Members | 1 day |
| 3.6 | ERD & Data Dictionary | Design conceptual ERD and document all database tables and fields. | Nabin | 2 days |
| 3.7 | Site Map & Wireframes | Design screen hierarchy and UI wireframes using Figma. | Dipti | 2 days |
| 3.8 | Review & Submission | Proofread and submit via HLMS by 26 June 2026. | All Members | 1 day |
| 4.0 | Iteration 1 Development | Implement UC1 (Register), UC2 (Inventory), UC3 (Browse). | All Members | 14 days |
| 4.1 | Database & Server Setup | Set up XAMPP, MySQL schema, and project folder structure. | Nabin | 2 days |
| 4.2 | UC1: User Auth Module | Register, login, email verification, 2FA, privacy settings. | Anurodh | 5 days |
| 4.3 | UC2: Food Inventory Module | Add, edit, delete, mark as used, convert to donation. | Nabin | 5 days |
| 4.4 | UC3: Browse Module | Browse, filter, claim donations, view item details. | Dipti | 4 days |
| 4.5 | Iteration 1 Testing | Unit and integration testing of UC1, UC2, UC3. | All Members | 3 days |
| 5.0 | Iteration 2Development | Implement UC4 (Analytics), UC5 (Notifications), UC6 (Meal Plan). | All Members | 14 days |
| 5.1 | UC4: Food Analytics Module | Visual dashboard: food saved chart, donation chart, filters. | Anurodh | 5 days |
| 5.2 | UC5: Notifications Module | Expiry alerts, donation updates, meal reminders (in-app + email). | Nabin | 5 days |
| 5.3 | UC6: Meal Planning Module | Weekly calendar, recipe suggestions, inventory reservation. | Dipti | 5 days |
| 5.4 | Iteration 2 Testing | Unit and integration testing of UC4, UC5, UC6. | All Members | 3 days |
| 6.0 | Final Testing & Bug Fixing | Full system testing, bug resolution, and performance checks. | All Members | 7 days |
| 7.0 | Final Documentation & Submission | Compile final report, source code, and submit all deliverables. | All Members | 5 days |

## 5.1 Milestones and Deliverables

| ID | Milestone | Deliverables | Date | Responsible |
| --- | --- | --- | --- | --- |
| M1 | Project initialization And started task one. | Team formed, GitHub repo created, case study reviewed | 22 May 2026 | All Members |
| M2 | Task 1 Submitted | Project Proposal / Project Plan document (this document) | 12 Jun 2026 | All Members |
| M3 | Task 2 Submitted | Requirements Specification and Design document | 26 Jun 2026 | All Members |
| M4 | Iteration 1 Complete | UC1 (Register), UC2 (Inventory), UC3 (Browse) developed and tested | 10 Jul 2026 | All Members |
| M5 | Iteration 2 Complete | UC4 (Analytics), UC5 (Notifications), UC6 (Meal Planning) developed and tested | 24 Jul 2026 | All Members |
| M6 | System Testing Complete | Full integration test report and bug fix log | 31 Jul 2026 | All Members |
| M7 | Final Submission | Complete project documentation, source code, and demo-ready system | 7 Aug 2026 | All Members |